## Slide 1: Network Analysis
Diagrammatic Representation of Activities and its predecessors.

## Slide 2: Topics to be covered
Terms used in network analysis,
Network or arrow diagram, Fulkerson’s rule,
Programme Evaluation and Review Technique (PERT),
Critical path method (CPM),
Time estimates for activities.
Probability of completion of project.
Determination of floats (total, free, independent & interfering) ,
Crashing of Simple Networks.

## Slide 3: Rules for Network Diagram (AOA)
Activity
Head Arrow
Tail Arrow
Denotes end of activity
Denotes starting of activity
Nodes representing events
1
2
A
Every Project or an activity will start from one single node and will end on one single node.

## Slide 4
1
A
B
C
Bursting Event
There can be more than one activity bursting out from one node but they cannot end on same node. They can end only on different nodes or a dummy arrow/ activity has to be created.

## Slide 5
4
1
2
3
Merging Event
More than one activity can end on one single node but they should have separate starting nodes or use dummy arrow/activity.

## Slide 6
1
2
A
B
Parallel activities are not allowed
Activities can go in from left to right only i,e the progress of the project can be depicted from left to right
S
B
A
Looping is not permitted

## Slide 7
Activity | Predecessor
A | -
B | A
C | A
D | B
E | C
A
B
C
D
E

## Slide 8
Activity | Predecessor
A | -
B | A
C | A
D | B
E | C
F | B
A
B
C
D
E
Every Project or an activity will start from one single node and will end on one single node.
F
Dangling of an activity is not allowed

## Slide 9
Activity | Predecessor
A | -
B | A
C | A
D | B
E | C
F | B
1
2
A
3
B
C
4
6
D
E
Every Project or an activity will start from one single node and will end on one single node.
F
5
Dangling of an activity is not allowed
Fulkerson’s Rule of Numbering

## Slide 10
Activity | Immediate predecessor
A | -
B | -
C | -
D | A
E | C
F | A
G | 
1
2
4
3
A
B
C
D
E
F
G
5

## Slide 11
Activity | Immediate predecessor
A | -
B | A
C | A
D | C
E | B,D
F | E
G | B,D
H | F,G
1
A
2
3
B
C
4
D
5
E
F
6
G
H
7

## Slide 12
Activity | Immediate predecessor
A | -
B | A
C | A
D | B,C
E | C
F | D
G | E
H | F,G
A
B
C
E
D
F
G

## Slide 13
Activity | Immediate predecessor
A | -
B | -
C | -
D | A,B
E | B,C
F | A,B
G | C
H | D,E,F
I | D
J | G
K | G
L | H,J
M | K
N | I,L
1
2
3
4
A
B
C
D
G
6
5
F
4
E
7
H
I
9
J
K
8
L
10
M
11
N

## Slide 14
Activity | Immediate predecessor | Expected completion Time (weeks)
A | - | 5
B | A | 2
C | A | 6
D | B | 12
E | D | 10
F | D | 9
G | D | 5
H | B | 9
I | C,E | 1
J | G | 2
K | F,I,J | 3
L | K | 9
M | H,G | 7
N | M | 8
1
A (5)
2
3
B (2)
C(6)
4
D (12)
5
6
E (10)
F(9)
G(5)
7
H(9)
I(1)
J(2)
8
K(3)
10
L(9)
M(7)
9
11
N(8)
Dummy(0)
1
0 | 
Forward pass Method
ES and EF
+ Time Duration
Consider all head arrows
Incase of any clash, consider max time element
A (10)
ES
EF/ES
10 | 
B
LS
LS/LF
Backward pass Method
LS and LF
- Time Duration
Consider all Tail arrows
Incase of any clash, consider min time element
Step 1
Step 2

## Slide 15
Activity | Immediate predecessor | Expected completion Time (weeks)
A | - | 5
B | A | 2
C | A | 6
D | B | 12
E | D | 10
F | D | 9
G | D | 5
H | B | 9
I | C,E | 1
J | G | 2
K | F,I,J | 3
L | K | 9
M | H,G | 7
N | M | 8
1
A (5)
2
3
B (2)
C(6)
4
D (12)
5
6
E (10)
F(9)
G(5)
7
H(9)
I(1)
J(2)
8
K(3)
10
L(9)
M(7)
9
11
N(8)
Dummy(0)
0 | 0
5 | 5
7 | 7
19 | 19
24 | 27
29 | 29
24 | 27
30 | 30
31 | 34
33 | 33
42 | 42
Critical Path is the longest path of the project. A project may have more than 1 critical path. Activities lying on critical path are known as critical activities.
Path |  | Duration
1-2-3-4-8-10-11 |  | 40 weeks
1-2-3-4-6-8-10-11 | A-B-D-E-I-K-L | 42 weeks
1-2-6-8-10-11 |  | 24 weeks
Critical Path

## Slide 16
Activity | Immediate predecessor | Expected completion Time (weeks)
A | - | 5
B | A | 2
C | A | 6
D | B | 12
E | D | 10
F | D | 9
G | D | 5
H | B | 9
I | C,E | 1
J | G | 2
K | F,I,J | 3
L | K | 9
M | H,G | 7
N | M | 8
1
A (5)
2
3
B (2)
C(6)
4
D (12)
5
6
E (10)
F(9)
G(5)
7
H(9)
I(1)
J(2)
8
K(3)
10
L(9)
M(7)
9
11
N(8)
Dummy(0)
0 | 0
5 | 5
7 | 7
19 | 19
24 | 27
29 | 29
24 | 27
30 | 30
31 | 34
33 | 33
42 | 42
Activity H- Total Float- Total surplus time available with the activity without delaying the project completion time.
H – 8 weeks
3-7-9-11=8+0+3=11 weeks
Activity H – free Float= Total surplus time available with the activity without delaying the succeeding activity
= 8 hours

## Slide 17
Activity | Immediate predecessor | Expected completion Time (weeks)
A | - | 5
B | A | 2
C | A | 6
D | B | 12
E | D | 10
F | D | 9
G | D | 5
H | B | 9
I | C,E | 1
J | G | 2
K | F,I,J | 3
L | K | 9
M | H,G | 7
N | M | 8
1
A (5)
2
3
B (2)
C(6)
4
D (12)
5
6
E (10)
F(9)
G(5)
7
H(9)
I(1)
J(2)
8
K(3)
10
L(9)
M(7)
9
11
N(8)
Dummy(0)
0 | 0
5 | 5
7 | 7
19 | 19
24 | 27
29 | 29
24 | 27
30 | 30
31 | 34
33 | 33
42 | 42
Events | Activity | Duration | Earliest |  | Latest |  | Total | HS | Free | TS | Independent | Interfering
 |  |  | Start | Finish | Start | Finish | Latest - earliest |  | Total float - HS |  | Free Float – Tail Slack | Total Float – Free Float
1-2 | A | 5 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0
2-3 | B | 2 | 5 | 7 | 5 | 7 | 0 | 0 | 0 | 0 | 0 | 0
2-6 | C | 6 | 5 | 11 | 23 | 29 | 18 | 0 | 18 | 0 | 18 | 0
3-4 | D | 12 | 7 | 19 | 7 | 19 | 0 | 0 | 0 | 0 | 0 | 0
3-7 | H | 9 | 7 | 16 | 18 | 27 | 11 | 3 | 8 | 0 | 8 | 3
4-5 | G | 5 | 19 | 24 | 22 | 27 | 3 | 3 | 0 | 0 | 0 | 3
4-6 | E | 10 | 19 | 29 | 19 | 29 | 0 | 0 | 0 | 0 | 0 | 0
4-8 | F | 9 | 19 | 28 | 21 | 30 | 2 | 0 | 2 | 0 | 2 | 0
5-7 | Dummy | 0 | 24 | 24 | 27 | 27 | 3 | 3 | 0 | 3 | -3= 0 | 3
5-8 | J | 2 | 24 | 26 | 28 | 30 | 4 | 0 | 4 | 3 | 1 | 0
6-8 | I | 1 | 29 | 30 | 29 | 30 | 0 | 0 | 0 | 0 | 0 | 0
7-9 | M | 7 | 24 | 31 | 27 | 34 | 3 | 3 | 0 | 3 | -3=0 | 3
8-10 | K | 3 | 30 | 33 | 30 | 33 | 0 | 0 | 0 | 0 | 0 | 0
9-11 | N | 8 | 31 | 39 | 34 | 42 | 3 | 0 | 3 | 3 | 0 | 0
10-11 | L | 9 | 33 | 42 | 33 | 42 | 0 | 0 | 0 | 0 | 0 | 0
Earliest Finish = Earliest Start + Duration
Latest start = Latest Finish – Duration
Total float = Latest - earliest, i.e LS – ES or LF – EF
Free Float = Total Float – Head Slack