## Slide 1: Network Analysis
Diagrammatic Representation of Activities and its predecessors.

## Slide 2: Rules for Network Diagram (AOA)
Activity
Head Arrow
Tail Arrow
Denotes end of activity
Denotes starting of activity
Nodes representing events
1
2
A
Every Project or an activity will start from one single node and will end on one single node.

## Slide 3
1
A
B
C
Bursting Event
There can be more than one activity bursting out from one node but they cannot end on same node. They can end only on different nodes or a dummy arrow/ activity has to be created.

## Slide 4
4
1
2
3
Merging Event
More than one activity can end on one single node but they should have separate starting nodes or use dummy arrow/activity.

## Slide 5
1
2
A
B
Parallel activities are not allowed
Activities can go in from left to right only i,e the progress of the project can be depicted from left to right
S
B
A
Looping is not permitted

## Slide 6
Activity | Predecessor
A | -
B | A
C | A
D | B
E | C
A
B
C
D
E

## Slide 7
Activity | Predecessor
A | -
B | A
C | A
D | B
E | C
F | B
A
B
C
D
E
Every Project or an activity will start from one single node and will end on one single node.
F
Dangling of an activity is not allowed

## Slide 8
Activity | Predecessor
A | -
B | A
C | A
D | B
E | C
F | B
1
2
A
3
B
C
4
6
D
E
Every Project or an activity will start from one single node and will end on one single node.
F
5
Dangling of an activity is not allowed
Fulkerson’s Rule of Numbering

## Slide 9
Activity | Immediate predecessor
A | -
B | -
C | -
D | A
E | C
F | A
G | 
1
2
4
3
A
B
C
D
E
F
G
5

## Slide 10
Activity | Immediate predecessor
A | -
B | A
C | A
D | C
E | B,D
F | E
G | B,D
H | F,G
1
A
2
3
B
C
4
D
5
E
F
6
G
H
7

## Slide 11
Activity | Immediate predecessor
A | -
B | A
C | A
D | B,C
E | C
F | D
G | E
H | F,G
A
B
C
E
D
F
G

## Slide 12
Activity | Immediate predecessor
A | -
B | -
C | -
D | A,B
E | B,C
F | A,B
G | C
H | D,E,F
I | D
J | G
K | G
L | H,J
M | K
N | I,L
1
2
3
4
A
B
C
D
G
6
5
F
4
E
7
H
I
9
J
K
8
L
10
M
11
N